S++++++ MASTER REPORT & ROADMAP AI Systems Engineering x Offensive Security September 2026 - September 2030 ¦ Generated 12 September 2026

Executive Audit Summary

Five fixes are enforced in this version, four requested plus one structural correction the requested four didn't cover: 1. 100% hyperlink coverage - every resource below is a live clickable link. 2. Hardware/compute tier per phase - specified per row, including RAM-bound phases GPU-only planning misses. 3. Academic freeze windows - a hard 2-week freeze is embedded before every UCP midterm/final block. 4. One flagship hybrid project per phase - no isolated, redundant builds remain. 5. Semester-reality correction - Phase 1 is rebuilt around actual Semester 5 courses (ML, AI, OS, InfoSec, SE) starting Sep 28, 2026, instead of generic content that would have re-created a known scheduling conflict.

Master Execution Table

| # | Phase & Timeline | Courses & Resources | Flagship Project | Compute Tier | Proof-of-Mastery Bar |
| --- | --- | --- | --- | --- | --- |
| 0 | Recall Sprint Sep 12-27, 2026 | CS50x MIT 6.006 SQLBolt | Secure Systems Utility Suite (TCP client/server, file-integrity checker, log analyzer, CLI DB app, HTTP server) | Local CPU / WSL2 - $0 | Reproduce and GDB-patch >=1 real memory/logic bug in your own C code |
| 1 | Semester 5 Fusion Sep 28, 2026 - Jan 2027 | Stanford CS229 Berkeley CS188 MIT 6.1810 (xv6) PortSwigger Academy OWASP WSTG MIT 18.06 MIT 18.05 | AI-Driven OS-Level Security Monitor - ML/AI anomaly detector instrumented into a modified xv6 kernel, WSTG-audited, SE-disciplined | Local CPU/WSL2 + GitHub Codespaces - $0-10/mo | Kernel extension traced live in a debugger; detector flags synthetic attacks with stated precision/recall; >=1 vuln remediated + report; full CI |
| 2 | Systems + Deep Learning Feb-Apr 2027 | Deep Learning Specialization fast.ai Stanford CS144 Linux Journey Windows Internals / Sysinternals | Autodiff NN Framework (CPU) + Network-Level Intrusion Detector | Local CPU/WSL2 + free Colab burst - $0-20/mo | Autodiff trains a real model without PyTorch; TCP stack interoperates live in Wireshark; detector documents features |
| 3 | CV/NLP + Web Security Depth May-Jul 2027 | Stanford CS231n Stanford CS224N PortSwigger Academy (advanced) OWASP WSTG | Self-Audited CV/NLP Web Application - full OWASP methodology pentest of your own deployed app | Colab / Codespaces GPU-lite - $20-40/mo | Full vulnerability class found, exploited, and patched with a formal pentest report |
| 4 | LLM + Binary Exploitation Aug-Oct 2027 | Stanford CS336 pwn.college | Transformer LLM + Binary Exploit Harness - from-scratch tokenizer/GPT paired with a self-introduced exploit | CLOUD GPU (RTX 4090/A100 via RunPod/Lambda) - $100-250/mo | Model generates coherent text; you independently execute a memory-corruption exploit you introduced yourself |
| 5 | MLOps + Reverse Engineering Nov 2027 - Jan 2028 | Stanford CS229S OST2 Ghidra | MLOps Serving Platform + Binary Audit | HARDWARE TRAP RAM-BOUND, not GPU-bound: 8GB local WILL bottleneck Ghidra+Docker+debugger - budget a cloud VM (16GB+) - $20-50/mo | Serving platform tracks drift + CI/CD live; binary fully decompiled & control-flow annotated with zero source access |
| 6 | Agents + Enterprise Security Feb-Apr 2028 | Hugging Face Agents Course AD Fundamentals (MS Learn) | Enterprise AI Agent Security Lab - tool-using agent tested against privilege escalation and prompt attacks | Cloud VM cluster (DC + workstation + attacker box) - $30-60/mo | >=3 distinct attack vectors executed against your own agent; boundaries patched and independently re-verified |
| 7 | FYP Integration May-Jun 2028 | University FYP Supervision | Thesis-Grade Research Artifact - hybrid AI system + security evaluation framework | Local + FYP-scope dependent | Publishable-quality report: threat model, baseline, ablations, open-source code |
| 8 | RL + Autonomous Security Agent Jul-Dec 2028 | Stanford CS224R | RL-driven agent that plans and executes multi-step security tests in a sandbox | Cloud GPU (RTX 4090/A100) - $100-200/mo | Agent completes test sequences with no hardcoded logic, evaluated against a benchmark you define |
| 9 | Formal Security + AI Red-Team Jan-Jun 2029 | MIT 6.1600 MITRE ATT&CK Training | AI Red-Team Lab + Secure RAG - adversarial ML harness, prompt-injection suite, isolated RAG | Local + Cloud GPU burst - $50-100/mo | Working exploit/defense pairs with measured improvement over an undefended baseline |
| 10 | Research Reproductions Jul-Dec 2029 | Scientific Writing Practice (USENIX Security / NeurIPS workshop targets) | 6 full paper reproductions with ablations | Local + Cloud GPU as each paper demands | Each writeup documents exact divergence from the original, failure modes, and your own ablations |
| 11 | Original Invention Jan-Sep 2030 | No further courses - original research only | Unified open-source AI-security system solving a real, unaddressed gap | Cloud GPU, scaled to final scope - $100-300/mo | Open-source release, working benchmarks, formal writeup, external users or citations |

Phase-by-Phase Deep Dives

Phase 0 - Recall Sprint (Sep 12-27, 2026)

Objective: Not new learning - cold recall of calculus, linear algebra, DSA, and OOP forgotten over the summer.

Balance: 100% foundational; no AI/security split yet.

Courses: CS50x  |  MIT 6.006  |  SQLBolt

Project: The Secure Systems Utility Suite doubles as recall vehicle and Phase 1 scaffolding.

Compute: Local only, zero cost.

Freeze window: None needed - pre-semester.

Phase 1 - Semester 5 Fusion (Sep 28, 2026 - Jan 2027)

Objective: Your transcript IS the union you're chasing this cycle - ML, AI, OS, InfoSec, SE all land in one semester.

Balance: ~60% university-anchored depth / 40% fusion build - a fixed 70/30 split doesn't apply cleanly when five subjects converge.

Courses: CS229  |  CS188  |  MIT 6.1810 (xv6)  |  PortSwigger  |  WSTG

Project: ML/AI anomaly-detection model -> instrumented into a syscall-audit extension added to xv6 -> attacked/audited via WSTG -> shipped with tests/CI/docs.

Compute: Local + free-tier Codespaces.

Freeze window: Hard 14-day freeze before UCP midterms (~mid-Nov) and finals (~mid/late Jan).

Phase 2 - Systems + Deep Learning (Feb-Apr 2027)

Objective: Deep learning fundamentals paired with networking depth the semester didn't cover.

Balance: 70% AI / 30% security.

Courses: Deep Learning Spec.  |  fast.ai  |  CS144  |  Linux Journey  |  Windows Internals

Project: Autodiff engine trains a real model without PyTorch; the TCP stack feeds a live intrusion detector.

Compute: Local, light Colab burst.

Freeze window: None (between semesters).

Phase 3 - CV/NLP + Web Security Depth (May-Jul 2027)

Objective: Applied perception/language models; security returns to full pentest methodology.

Balance: 70% AI / 30% security.

Courses: CS231n  |  CS224N  |  PortSwigger (advanced)  |  WSTG

Project: Deploy the CV/NLP app, then run a full self-pentest against it.

Compute: Colab/Codespaces GPU-lite.

Freeze window: None (summer).

Phase 4 - LLM + Binary Exploitation (Aug-Oct 2027)

Objective: The first genuinely compute-heavy phase.

Balance: 60% AI / 40% security - CS336 and pwn.college are each substantial alone.

Courses: CS336  |  pwn.college

Project: Train a real tokenizer/GPT model, then independently exploit a bug introduced into your own compiled inference server.

Compute: Cloud GPU rental - the real RTX 4090/A100-tier phase.

Freeze window: 14 days before semester 6 midterms if the academic calendar overlaps - verify before locking dates.

Phase 5 - MLOps + Reverse Engineering (Nov 2027 - Jan 2028)

Objective: Production ML discipline plus deep RE.

Balance: 50% / 50%.

Courses: CS229S  |  OST2  |  Ghidra

Project: A monitored serving platform, plus a from-scratch Ghidra decompilation of one of your own binaries.

Compute:  RAM TRAP  RAM-bound, not GPU-bound: 8GB will thrash under Ghidra+Docker+debugger concurrently - budget a cloud VM.

Freeze window: Hard freeze before finals (~Jan).

Phase 6 - Agents + Enterprise Security (Feb-Apr 2028)

Objective: Autonomous agents meet enterprise identity/security.

Balance: 50% / 50%.

Courses: HF Agents Course  |  AD Fundamentals

Project: An internal agent attacked across >=3 vectors inside your own AD lab.

Compute:  RAM TRAP  Multi-VM cloud cluster required - a single 8GB machine cannot run DC + workstation + attacker box concurrently.

Freeze window: Check semester 6/7 boundary for overlap.

Phase 7 - FYP Integration (May-Jun 2028)

Objective: Convert the degree requirement into a hybrid research artifact rather than a disconnected capstone.

Balance: Determined by FYP scope.

Project: Whatever FYP scope your supervisor approves, framed as threat-model -> baseline -> implementation -> evaluation.

Compute: Local + FYP-scope dependent.

Freeze window: Per university FYP calendar.

Phase 8 - RL + Autonomous Security Agent (Jul-Dec 2028)

Objective: Post-graduation; tracks converge toward research.

Balance: AI-led, security-informed.

Courses: CS224R

Project: An RL agent that plans multi-step security tests without hardcoded rules.

Compute: Cloud GPU.

Freeze window: None (post-grad).

Phase 9 - Formal Security + AI Red-Team (Jan-Jun 2029)

Objective: Formal security foundations meet adversarial ML.

Balance: 50% / 50%.

Courses: MIT 6.1600  |  MITRE ATT&CK

Project: Adversarial ML + secure RAG with measured defense improvements.

Compute: Local + Cloud GPU burst.

Freeze window: None (post-grad).

Phase 10 - Research Reproductions (Jul-Dec 2029)

Objective: Demonstrate research capability, not just claim it.

Balance: Research-only.

Project: 6 full paper reproductions, each with a documented divergence/failure analysis.

Compute: Local + Cloud GPU as each paper demands.

Freeze window: None (post-grad).

Phase 11 - Original Invention (Jan-Sep 2030)

Objective: The terminal proof the four years compounded into something, not just a transcript.

Balance: Original research only.

Project: One unified open-source system at the AI x security intersection, with real external adoption or citation.

Compute: Cloud GPU, scaled to final scope.

Freeze window: None (post-grad).

The S++++++ Proof-of-Mastery Protocol

A phase is never marked complete on lecture-completion or course-certificate grounds. The non-negotiable exit sequence applies to every flagship project in this report:

Terminal Exit Sequence 1. Derive: Reconstruct the underlying math/logic from first principles, unaided. 2. Implement: Build it from scratch - no wrapping an existing library and calling it done. 3. Benchmark: Compare against a real, independent standard (NumPy, scikit-learn, a published CVE, an undefended baseline) with a stated numeric bar. 4. Break: Attack or stress your own implementation until it fails. 5. Patch: Fix the break, then re-attack to confirm the fix actually holds. 6. Document: A written artifact another engineer could audit without asking you questions.

Skipping any of the six stages means the phase is not S++++++ regardless of course-completion status.